## NFT- RA
NFT - Risk Assessment
S.No | Project Name | Scope/feature | Functional Changes | Hardware Changes | Software Changes | Impact of Downtime | Load/Voluem Changes | Risk Score | Justification
1 | Plasma Donor v1 | New | High | No Changes | Moderate | Considerable time taken to insert into DB | No Changes | ORANGE | Adding this feature makes is coherant with features like adding group and hence, functional changes is high
2 | Plasma Donor v2 | Existing | Moderate | No changes | Moderate | Faster DB operations | NO changes | ORANGE | Updated SQL statements for faster DB operations
NFT - Detailed Test Plan
|  |  | S.No | Project Overview | NFT Test approach | Assumptions/Dependencies/Risks | Approvals/SignOff
|  |  | 1 | Plasma Donor v1 | Load testing | Locust installed,app deployed with docker
|  |  | 2 | Plasma Donor v2 | Stress testing | Locust installed,app deployed with docker
|  |  | 3 | Plasma Donor v3 | Spike testing | Locust installed,app deployed with docker
|  |  | 4 | Plasma Donor v4 | Reliability Testing | Locust installed,app deployed with docker
End Of Test Report
S.No | Project Overview | NFT Test approach | NFR - Met | Test Outcome | GO/NO-GO decision | Recommendations | Identified Defects (Detected/Closed/Open) | Approvals/SignOff
1 | Plasma Donor v1 | Load testing | Failures | Number of failures spikes from 0.3 to 0.9 with increase in number of users from 70 to 100 | GO | Provide checks from input value before inserting into database | Bad request error on adding expense without primary,required rows
2 | Plasma Donor v2 | Stress testing | Response time | Increases from 3100 for one user to 1900ms for 20 users | Go
3 | Plasma Donor v3 | Spike testing | Response time | Varies from minimum if 1367 ms and maximum of 25609ms for a specific feature of adding expenses | Go
4 | Plasma Donor v4 | Reliability Testing | No of failures | 41% failures with adding expense with spike in user data and incorrect input values, but maintained aveage of 13000ms response timne | Go | Provide checks from input value before inserting into database | Internal server error on adding expense without primary, required rows

## DTP
NFT Test approach
Load Test

## Testdata (hidden)
New | No Changes | No Changes | RED | In-Scope | Baseline Test Approach
Existing | Low | >5 to 10% | ORANGE | Out of Scope | Benchmark Test Approach
| Moderate | >10 to 30% | GREEN
| High | >30 to 50 %
>50 to 70%
>70 to 100%